## Estimate
Cost estimate (USD thousands)
Item | Most likely | Cost
Site work | 120 | 120
Foundation | 340 | 340
Structure | 820 | 820
MEP | 610 | 610
Finishes | 450 | 450
Equipment | 280 | 280
Risk event | Probability | Impact | Occurs | Cost
Ground conditions | 0.25 | 150 | 0
Design change | 0.35 | 90 | 0
Supplier delay | 0.2 | 60 | 0
Severe weather | 0.3 | 40 | 0
Base estimate
Total cost
Budget | 2900
Over budget

## Schedule
Activity | Most likely (weeks) | Duration
Design | 8 | 8
Permits | 6 | 6
Foundation | 10 | 10
Structure | 16 | 16
MEP | 12 | 12
Finishes | 10 | 10
Commissioning | 3 | 3
Weather delay (weeks)
Finish (weeks)
Deadline | 60