## Estimate
Cost estimate (USD thousands), written for @RISK
Item | Min | Most likely | Max | Cost | Correlation | Structure | MEP
Site work | 100 | 120 | 170 |  | Structure | 1
Foundation | 300 | 340 | 460 |  | MEP | 0.6 | 1
Structure | 760 | 820 | 1010
MEP | 540 | 610 | 780
Finishes | 400 | 450 | 560
Equipment | 260 | 280 | 330
Risk event | Probability | Impact | Occurs | Cost
Ground conditions | 0.25 | 150
Design change | 0.35 | 90
Supplier delay | 0.2 | 60
Severe weather | 0.3 | 40
Total cost
Budget (one per simulation)
Over budget
Mean total cost (after a run)

## Demonstrations
What the importer converts and what it leaves (nothing in the estimate uses these formulas)
Written as | Formula
A distribution inside a larger formula
An argument that is a calculation
A risk event in one cell
A compound distribution
A PERT given by percentiles